## Slide 1
IMPLEMENTATION ROADMAP
PlacementHub
A phased, low-risk path for colleges to adopt PlacementHub
without disrupting existing placement processes.
8-week rollout · 7 phases · Continuous improvement

## Slide 2
PLACEMENTHUB
02 / 15
PURPOSE
Implementation Objective
Enable colleges to adopt PlacementHub in a phased, low-risk manner — with quick adoption, measurable outcomes, and continuous improvement.
01
Quick adoption
Clear weekly milestones from kickoff to go-live
02
Low operational risk
Pilot first, then expand — no big-bang cutover
03
Measurable outcomes
Adoption, operations, and quality tracked from day one

## Slide 3
PLACEMENTHUB
03 / 15
OVERVIEW
Seven-Phase Implementation Timeline
01
Week 1
Discovery & Kickoff
Demo, plan, nominate coordinator
02
Week 2
Platform Config
College, users, depts, courses
03
Week 3
Student Onboarding
Import, verify, train students
04
Week 4
Employer Setup
Recruiters & company database
05
Weeks 5–6
Pilot Drive
First live placement drive
06
Weeks 7–8
Campus Rollout
Full placement activities
07
Ongoing · Continuous Improvement
Training, analytics, AI enhancements

## Slide 4
PLACEMENTHUB
04 / 15
PHASE
01
Week 1
Discovery &
Kickoff
Introduction & Planning
ACTIVITIES
Conduct online product demonstration
Map current placement workflow
Identify TPOs and faculty coordinators
Finalize implementation timeline
Nominate PlacementHub coordinator
DELIVERABLES
Kickoff meeting completed
Implementation schedule approved
Admin credentials shared

## Slide 5
PLACEMENTHUB
05 / 15
PHASE
02
Week 2
Platform
Configuration
College setup & user model
ACTIVITIES
College profile & academic years
Departments, courses, branches
Placement eligibility rules
Placement policies
Administrator & faculty accounts
DELIVERABLES
Platform configured
User accounts created
Initial validation completed

## Slide 6
PLACEMENTHUB
06 / 15
PHASE
03
Week 3
Student
Onboarding
Import, verify, activate the student portal
ACTIVITIES
Import student database
Verify student information
Upload resumes & complete profiles
Verify email addresses
Train students on PlacementHub
DELIVERABLES
Student database imported
Student portal activated
Onboarding completed

## Slide 7
PLACEMENTHUB
07 / 15
PHASE
04
Week 4
Employer
Setup
Recruiters, companies, job templates
ACTIVITIES
Create recruiter accounts
Add existing recruiters
Configure employer database
Create company profiles
Configure job posting templates
DELIVERABLES
Recruiter portal activated
Employer database configured

## Slide 8
PLACEMENTHUB
08 / 15
PHASE
05
Weeks 5–6
Pilot
Placement Drive
One or two live drives through PlacementHub
ACTIVITIES
Publish company requirements
Student registrations
Eligibility verification & shortlisting
Interview scheduling
Offer management & reporting
DELIVERABLES
Successful pilot drive
User feedback collected
Improvements documented

## Slide 9
PLACEMENTHUB
09 / 15
PHASE
06
Weeks 7–8
Campus-wide
Rollout
Transition all placement activities to PlacementHub
Student Management
Recruiter Management
Placement Drives
Internship Management
Resume Database
Interview Scheduling
Offer Tracking
Placement Reports
Analytics Dashboard
Communication Portal
DELIVERABLES
Complete rollout completed · Operational support initiated

## Slide 10
PLACEMENTHUB
10 / 15
PHASE
07
Ongoing
Continuous
Improvement
Quarterly roadmap · Adoption reports · Usage analytics
Monthly cadence after go-live
01
Review meetings
Alignment on progress and blockers
02
User feedback
Collect insights from teams & students
03
Feature enhancements
Prioritize and ship improvements
04
AI-powered upgrades
Adopt smarter placement tooling
05
Product updates
Stay current with platform releases
06
User training
Keep campus teams confident

## Slide 11
PLACEMENTHUB
11 / 15
PARTNERSHIP
Shared Responsibilities
PLACEMENTHUB TEAM
Product setup
Platform configuration
Training
Technical support
Product updates
Bug fixes
Feature enhancements
COLLEGE
Nominate implementation coordinator
Share student database
Define placement policies
Coordinate faculty members
Student onboarding
Recruiter engagement
Feedback and testing

## Slide 12
PLACEMENTHUB
12 / 15
SCHEDULE
Suggested 8-Week Timeline
W1
Kickoff & Planning
W2
Platform Configuration
W3
Student Import & Training
W4
Recruiter Setup
W5
Pilot Placement Drive
W6
Pilot Review
W7
Campus Rollout
W8
Go Live

## Slide 13
PLACEMENTHUB
13 / 15
OUTCOMES
Success Metrics
ADOPTION
100%
Placement team onboarded
100%
Student records imported
>90%
Student profile completion
>80%
Recruiter onboarding
OPERATIONAL
First drive completed successfully
Less spreadsheet dependency
Faster student communication
Faster recruiter coordination
Automated reporting
QUALITY
User satisfaction
Drive success rate
System adoption rate
Active recruiters
Student applications
Admin time saved

## Slide 14
PLACEMENTHUB
14 / 15
NEXT HORIZON
Long-Term Vision — 3 to 6 Months
After core platform success, progressively adopt advanced modules.
AI FEATURES
AI Resume Analysis
AI Resume Builder
AI Interview Prep
AI Career Guidance
AI Skill Gap Analysis
PLACEMENT
Internship Management
Placement Analytics
Employer CRM
Alumni Engagement
Drive Automation
ACADEMIC
Industry Projects
Hackathons
Skill Assessments
Student Portfolio
NAAC / NBA Support

## Slide 15
IMPLEMENTATION PHILOSOPHY
Phased adoption. Minimal disruption.
Maximum long-term success.
End-to-end digitization
Centralized student database
Improved employer engagement
Faster placement operations
Better analytics & transparency
Reduced manual effort
Better student experience
AI-assisted management
Start with a pilot · prove value · expand with confidence