## Slide 1
⚠
PROJECT MANAGEMENT · MODULE 4
Risk
Management
Managing Uncertainty in Projects
Identifying, assessing, prioritising, and responding to project risks — from register to contingency.
RISK MANAGEMENT
01 / 45

## Slide 2
Learning Objectives
SESSION MAP
01
Define risk
Understand what a project risk is and why it matters
02
Risk vs Issue
Distinguish between a risk and an active problem
03
Identify risks
Apply structured techniques to surface what could go wrong
04
Assess P × I
Rate probability, impact, and calculate a risk score
05
Risk Register
Create and maintain the central risk log
06
Risk Responses
Select appropriate strategies: Avoid, Mitigate, Transfer, Accept
07
Mitigation & Contingency
Plan before and after a risk occurs
08
Residual & Secondary
Understand risks that survive or are created by responses
09
Monitor
Keep risk management alive throughout the project lifecycle
10
Opportunities
Recognise that positive uncertainty is also a risk to manage
RISK MANAGEMENT
02 / 45

## Slide 3
CORE CONCEPT
What is a Project Risk?
Risk = Uncertainty that can affect project objectives
A risk is an uncertain event or condition that, if it occurs, can have a positive or negative effect on the project.
01
Scope
02
Schedule
03
Cost
04
Quality
05
Performance
06
Objectives
KEY WORD
UNCERTAINTY
RISK MANAGEMENT
03 / 45

## Slide 4
Risk is Not Always Bad
TYPES OF UNCERTAINTY
THREAT
Negative risk
Something that could harm the project.
→ Increases cost or delays schedule
→ Reduces quality or performance
→ Jeopardises project objectives
→ Must be actively managed
OPPORTUNITY
Positive risk
Something that could benefit the project.
→ Reduces cost or compresses schedule
→ Improves quality or performance
→ Advances project goals
→ Should also be actively managed
Example:
AI automation could reduce development time by 30% — this is an opportunity, not a threat.
RISK MANAGEMENT
04 / 45

## Slide 5
Risk vs Issue
KEY DISTINCTION
RISK
ISSUE
May happen
Has happened
Future uncertainty
Current problem
Probability matters
Probability no longer matters
Managed through risk response
Managed through issue resolution
Logged in Risk Register
Logged in Issue Log
Risk → What might happen? | Issue → What has happened?
RISK MANAGEMENT
05 / 45

## Slide 6
PAUSE & REFLECT
Risk or Issue? The PM's most common existential crisis.
RISK MANAGEMENT
06 / 45

## Slide 7
WORKED EXAMPLE
Risk → Issue: The Transition
THE RISK
Developer may leave
Developer may leave during the development phase.
Probability: 3/5 | Impact: 5/5 | Score: 15
THE TRIGGER
Warning sign appears
Developer submits notice or interview activity is detected.
This is the trigger — risk is about to materialise.
THE ISSUE
Developer has resigned
The uncertain event has now occurred.
Probability is irrelevant — this is an active problem.
Discussion — At what precise moment did the risk become an issue?
RISK MANAGEMENT
06 / 45

## Slide 8
Why Do Projects Have Risks?
SOURCES OF UNCERTAINTY
Projects operate in conditions of uncertainty. The more uncertainty, the greater the need for active risk management.
New technology
Unproven tools introduce unknown failure modes
Limited information
Decisions made with incomplete data
Changing requirements
Scope creep opens new risk windows
Limited resources
Constraints on budget, people, or time
Tight deadlines
Compressed schedules reduce tolerance for delays
Human dependencies
Key-person reliance creates fragile single points
Vendor dependencies
External suppliers add variability
Regulatory changes
New laws can invalidate plans mid-project
Market changes
Customer behaviour or competition shifts
RISK MANAGEMENT
07 / 45

## Slide 9
RISK TAXONOMY
Sources of Project Risk
INTERNAL
People
Technology
Processes
Budget
Schedule
Quality
Communication
Organisational changes
EXTERNAL
Vendors
Customers
Competitors
Regulations
Economy
Weather
Political environment
Market conditions
RISK MANAGEMENT
08 / 45

## Slide 10
Risk Categories
CLASSIFICATION FRAMEWORK
Technical
· Technology failure
· Integration problems
Schedule
· Delayed activities
· Dependencies
Cost
· Budget overrun
· Price increases
People
· Attrition
· Skills shortage
Vendor
· Supplier failure
· Delivery delays
Customer
· Changing requirements
· Low adoption
Regulatory
· New laws
· Compliance requirements
RISK MANAGEMENT
09 / 45

## Slide 11
RISK IDENTIFICATION
How to Identify Risks
What could prevent us from achieving the project objectives?
Brainstorming
Structured group discovery sessions
Interviews
One-on-one expert sessions
Checklists
Industry-standard risk libraries
Historical data
Past project lessons and registers
SWOT Analysis
Strengths, Weaknesses, Opportunities, Threats
Root-cause Analysis
Identify underlying causes of potential failures
Assumption Analysis
Challenge every project assumption
Scenario Analysis
"What if" planning for key variables
Expert Judgment
Bring in specialist knowledge
Lessons Learned
Apply organisation's prior experience
Important: Risk identification is continuous — it does not stop after the first workshop.
RISK MANAGEMENT
10 / 45

## Slide 12
REALITY CHECK
"We didn't think that could happen." — Famous last words on every failed project.
RISK MANAGEMENT
11 / 45

## Slide 13
How to Write a Good Risk
RISK STATEMENT
WEAK
Database problem
No cause, no event, no impact. Impossible to act on.
BETTER
Database performance may deteriorate during peak usage.
Identifies the event but lacks the causal chain.
STRONG
If database performance deteriorates during peak usage, application response time may increase and negatively affect user experience and adoption.
Cause → Risk Event → Impact. Fully actionable.
Structure: Cause → Risk Event → Impact
RISK MANAGEMENT
11 / 45

## Slide 14
RISK ASSESSMENT
Understanding Probability
Probability = How likely is the risk to occur?
5
Very High
80–100%
4
High
60–79%
3
Medium
40–59%
2
Low
20–39%
1
Very Low
0–19%
Example
70%
Probability of vendor delay
Rating: 4 / High
Note: Scales should match project context.
RISK MANAGEMENT
12 / 45

## Slide 15
Understanding Impact
RISK ASSESSMENT
Impact = What happens if the risk occurs? Consider all affected dimensions.
₹
Cost
Budget overrun, unplanned expenditure
⏱
Schedule
Delays, milestone slippage
◉
Scope
Missing deliverables, feature gaps
★
Quality
Defects, rework, performance drop
⚐
Reputation
Customer satisfaction, brand trust
⚡
Performance
System speed, user experience
EXAMPLE IMPACT
Risk: Payment gateway integration is delayed. → Impact: Product launch delayed by 3 weeks.
RISK MANAGEMENT
13 / 45

## Slide 16
RISK SCORING
Probability × Impact
RISK SCORE
Probability × Impact
A simple and widely used method for prioritising risks based on combined likelihood and consequence.
Probability
4
High
×
Impact
5
Very High
=
Risk Score
20
High Priority
Higher score = Higher priority. Focus management attention and resources on the risks that matter most.
RISK MANAGEMENT
14 / 45

## Slide 17
Probability–Impact Matrix
RISK PRIORITISATION TOOL
Impact →
1
Very Low
2
Low
3
Medium
4
High
5
Very High
5 Very High
5
10
15
20
25
4 High
4
8
12
16
20
3 Medium
3
6
9
12
15
2 Low
2
4
6
8
10
1 Very Low
1
2
3
4
5
Probability
↓
≥16 · HIGH
9–15 · MEDIUM
4–8 · LOW – WATCH
≤3 · LOW
Discussion — Which risks should receive immediate attention?
RISK MANAGEMENT
15 / 45

## Slide 18
RISK SCORING IN PRACTICE
Scoring risks: 90% structured analysis, 10% gut feeling, 100% disputed in the meeting.
Source: Every project team ever.
RISK MANAGEMENT
16 / 45

## Slide 19
RISK LESSON
Probability Alone Is Not Enough
RISK A
Probability
90%
Impact
₹10,000
Low Impact — Low Priority
RISK B
Probability
10%
Impact
₹10 lakh
High Impact — HIGH Priority
A low-probability risk can still be HIGH PRIORITY if its impact is catastrophic.
RISK MANAGEMENT
16 / 45

## Slide 20
Risk Prioritisation
FOCUS ALLOCATION
Not every risk deserves equal management attention. Focus resources on what matters most.
HIGH
Immediate action required
· High probability + High impact
· Scores typically 16–25
· Dedicated owner and response plan
MEDIUM
Monitor and plan response
· Moderate probability or impact
· Scores typically 6–15
· Response plan ready, monitor trigger
LOW
Accept and log
· Low probability + Low impact
· Scores typically 1–5
· Log, review periodically, no active plan
Project Manager's role: Focus resources on the risks that matter most.
RISK MANAGEMENT
17 / 45

## Slide 21
RISK REGISTER
The Risk Register
The central living document that records all identified risks and their management details.
Risk ID
Unique identifier for tracking and reference
Risk Description
Clear Cause → Event → Impact statement
Category
Technical / Schedule / Cost / People / Vendor / Customer / Regulatory
Probability
Rated 1–5 (or percentage) — how likely?
Impact
Rated 1–5 — how severe if it occurs?
Risk Score
Probability × Impact for prioritisation
Risk Owner
Named person responsible for monitoring and response
Response Strategy
Avoid / Mitigate / Transfer / Accept
Mitigation Actions
Steps taken before the risk occurs
Trigger
Early warning sign that the risk is approaching
Contingency Plan
What we do if the risk occurs
Status
Open / Active / Closed / Monitoring
RISK MANAGEMENT
18 / 45

## Slide 22
Example Risk Register
PLACEMENT MANAGEMENT SYSTEM
ID
Risk
Cat
P
I
Score
Owner
Response
R01
Payment gateway integration delay
Tech
4
5
20
Tech Lead
Mitigate
R02
Developer resigns mid-project
People
3
5
15
PM
Mitigate
R03
Customer changes scope
Customer
4
4
16
PM
Avoid / Mitigate
R04
Vendor price increase
Vendor
2
4
8
Procurement
Transfer
R05
Data quality issues with student data
Data
3
3
9
BA
Mitigate
Discussion — Which risk would you bring up first in the project status meeting — and why?
RISK MANAGEMENT
19 / 45

## Slide 23
ACCOUNTABILITY
The Risk Owner
RISK OWNER
Named person responsible for managing a specific risk throughout its lifecycle.
Monitor the risk for changes in probability or impact
Watch for triggers that signal the risk is approaching
Implement the agreed response strategy
Escalate promptly when the trigger fires or conditions worsen
Ensure contingency actions are completed on time
EXAMPLE
Cloud infrastructure
failure
Risk Owner:
Infrastructure Lead
KEY POINT
If nobody owns the risk, it is unlikely to be managed effectively.
RISK MANAGEMENT
20 / 45

## Slide 24
Risk Trigger
EARLY WARNING SYSTEM
TRIGGER DEFINITION
A trigger is an early warning sign that tells us: this risk may be about to happen.
RISK
Vendor may miss delivery deadline
TRIGGER
Vendor misses two consecutive milestones or requests a schedule extension
RESPONSE
Escalate to vendor manager, activate contingency sourcing options
RISK
Project may exceed budget
TRIGGER
80% of budget consumed but only 60% of work completed
RESPONSE
Emergency cost review, scope reduction options, request additional budget
RISK
Developer may leave the project
TRIGGER
Developer begins working reduced hours or submits fewer commits
RESPONSE
Private conversation with PM, knowledge transfer initiated
RISK MANAGEMENT
21 / 45

## Slide 25
THE FOUR RESPONSES EXPLAINED HONESTLY
Mitigate: reduce it. Avoid: sidestep it. Transfer: make it someone else's problem. Accept: pray.
RISK MANAGEMENT
22 / 45

## Slide 26
RISK RESPONSE STRATEGIES
Responding to Threats
01
Avoid
Change the plan so the risk no longer exists.
HOW
Modify scope, timeline, or approach to eliminate the risk entirely.
EXAMPLE
Use a proven API instead of custom-building a risky integration.
02
Mitigate
Reduce the probability or impact of the risk.
HOW
Take early action to make the risk less likely or less damaging.
EXAMPLE
Conduct load testing before launch to reduce performance risk.
03
Transfer
Move the financial or operational risk to another party.
HOW
Insurance, contracts, fixed-price agreements, or specialist vendors.
EXAMPLE
Fixed-price SLA with a vendor for mission-critical delivery.
04
Accept
Acknowledge the risk without active intervention.
HOW
Log it, monitor it, and activate contingency if it occurs.
EXAMPLE
Accept minor delays from public holidays with buffer in schedule.
RISK MANAGEMENT
22 / 45

## Slide 27
Applying Threat Responses
WORKED EXAMPLE
RISK
New technology may not perform as expected under production conditions.
Avoid
Use proven, battle-tested technology instead.
Eliminates the risk entirely but may limit innovation.
Mitigate
Build a working prototype before committing to full development.
Reduces probability by gathering evidence early.
Transfer
Engage a specialist vendor with performance guarantees in the SLA.
Shifts financial risk to a third party.
Accept
Proceed with the technology and monitor performance post-launch.
Appropriate only when risk score is low or opportunity outweighs threat.
Discussion — Which response would you choose for this risk, and why?
RISK MANAGEMENT
23 / 45

## Slide 28
OPPORTUNITY RESPONSES
Responding to Opportunities
Positive risks are opportunities — they should be actively pursued, not ignored.
01
Exploit
Ensure the opportunity definitely occurs.
Dedicate resources specifically to make it happen.
Assign best developers to AI integration to guarantee the speed gain.
02
Enhance
Increase the probability or magnitude of the benefit.
Add resources or change approach to amplify the positive outcome.
Add a second AI specialist to accelerate the gain further.
03
Share
Partner with another party to maximise the benefit.
Joint venture, partnership, or resource sharing arrangement.
Co-develop the AI module with a vendor who has specialised capability.
04
Accept
Take advantage if it occurs without pursuing it.
No proactive action — benefit from it if it happens naturally.
If the library update speeds things up, great. No action needed now.
RISK MANAGEMENT
24 / 45

## Slide 29
Mitigation vs Contingency
PLANNING BOTH
MITIGATION
Before the risk occurs
What can we do to reduce the probability or impact?
Proactive action taken in advance
Reduces probability, impact, or both
Part of the Risk Register from the start
May reduce risk score significantly
CONTINGENCY
If the risk occurs
What will we do when the trigger fires?
Reactive plan activated by the trigger
Deals with consequences after the event
Contingency budget may be reserved
Transforms into an Issue Response Plan
Memory trick —
Mitigation = BEFORE · Contingency = AFTER
RISK MANAGEMENT
25 / 45

## Slide 30
RESIDUAL RISK
What Remains After the Response
INITIAL RISK
80%
System downtime probability
before any action
MITIGATION
→
Introduce redundant
infrastructure, failover, backups
RESIDUAL RISK
20%
Remaining probability
after mitigation is applied
Residual Risk
Risk that remains after a response has been implemented. Must still be monitored.
RISK MANAGEMENT
26 / 45

## Slide 31
Secondary Risk
UNINTENDED CONSEQUENCES
A response to one risk can create a new risk. Every response must itself be assessed.
ORIGINAL RISK
Internal team lacks specialised expertise
↓
RESPONSE
Hire an external consultant
↓
SECONDARY RISK
Consultant may become unavailable or leave mid-project
↓
NEW RESPONSE
Knowledge transfer plan, backup consultant identified
Key lesson: Risk responses themselves must be assessed for the new risks they create.
RISK MANAGEMENT
27 / 45

## Slide 32
QUALITATIVE ANALYSIS
Qualitative Risk Analysis
Question: Which risks deserve management attention first?
Probability
How likely is the risk to occur?
Impact
How severe would the consequences be?
Urgency
How quickly might the risk materialise?
Proximity
How close in time is it to the project's current phase?
Manageability
How much control does the team have over this risk?
Connectivity
Is this risk linked to or driven by other risks?
OUTPUT
Prioritised Risk List → Focus for detailed planning, owner assignment, and response development
RISK MANAGEMENT
28 / 45

## Slide 33
Quantitative Risk Analysis
NUMERICAL ESTIMATION
Quantitative analysis attempts to numerically estimate the overall effect of risk on project outcomes.
EMV
Expected Monetary Value
Probability × Financial Impact. Quantifies the average expected cost or gain from a risk.
DTA
Decision Tree Analysis
Maps decisions and risk events to compare options and expected outcomes numerically.
MCS
Monte Carlo Simulation
Runs thousands of simulations varying uncertain inputs to produce probability distributions for schedule or cost.
SA
Statistical Analysis
Uses historical data and statistical models to estimate likely ranges for cost, schedule, or quality.
Quick EMV example:
Probability 20% × Impact ₹10 lakh = EMV ₹2 lakh (expected value of the uncertainty, not a guaranteed loss)
RISK MANAGEMENT
29 / 45

## Slide 34
EXPECTED MONETARY VALUE
EMV = Probability × Financial Impact
Probability
0.20
20%
×
Impact
₹10L
10 lakh
=
EMV
₹2L
Expected value
WHAT EMV IS
The statistical average value of uncertainty — how much we should notionally set aside for this risk across many similar projects.
WHAT EMV IS NOT
A guarantee that we will lose ₹2 lakh. EMV is a planning tool, not a prediction. The actual outcome is binary — the risk either occurs or it does not.
RISK MANAGEMENT
30 / 45

## Slide 35
THE CYCLE CONTINUES
Risk monitoring never stops. Not on Fridays. Not on holidays. Not ever.
Welcome to project management.
RISK MANAGEMENT
31 / 45

## Slide 36
Risk Appetite, Tolerance & Threshold
ORGANISATIONAL CONTEXT
RISK APPETITE
How much risk are we willing to accept?
A strategic, organisation-level decision about the acceptable level of uncertainty in pursuit of objectives.
"We are willing to accept moderate technology risk in order to remain competitive."
RISK TOLERANCE
How much variation can we absorb?
The project-level boundary — how far from plan is acceptable before action is required.
"We can tolerate a maximum 5-day schedule delay and ₹50,000 cost overrun."
RISK THRESHOLD
When must we act or escalate?
The specific trigger point at which the project manager or sponsor must take action or escalate.
"If cost variance exceeds 10%, an emergency review is mandatory."
RISK MANAGEMENT
31 / 45

## Slide 37
MONITORING & CONTROL
Risk Monitoring
Risk management does not stop after the Risk Register is created. Review at every status meeting.
?
Has the probability changed?
?
Has the impact changed?
?
Has the trigger appeared?
?
Is the mitigation working?
?
Has the risk occurred — is it now an issue?
?
Have new risks emerged?
?
Has the residual risk changed?
?
Does leadership or the sponsor need to act?
Log every change. Update scores, owners, and responses. Close risks that no longer apply.
RISK MANAGEMENT
32 / 45

## Slide 38
The Risk Management Cycle
CONTINUOUS PROCESS
IDENTIFY
ANALYSE
PRIORITISE
RESPOND
MONITOR
IDENTIFY
NEW RISKS
REPEAT
CONTINUOUSLY
Risk management is a continuous process — it never stops until the project closes.
RISK MANAGEMENT
33 / 45

## Slide 39
CASE STUDY
College Placement Management System
A college is implementing a new digital placement platform. Identify and prioritise the following risks.
01
Requirements may change
Customer
02
Developer may leave
People
03
Student data may be incorrect
Data
04
Third-party API may fail
Technical
05
College approval may be delayed
Regulatory
06
Student adoption may be low
Customer
07
Cybersecurity incident may occur
Technical
08
AI improves dev productivity
Opportunity
Your task: Rate each risk for Probability (1–5), Impact (1–5), and Score. Then select a response and owner.
RISK MANAGEMENT
34 / 45

## Slide 40
Classroom Exercise
YOUR TASK
For each of the eight risks in the case study, complete the following analysis.
1
Probability
Rate 1–5: How likely is this risk?
2
Impact
Rate 1–5: How severe if it occurs?
3
Risk Score
Calculate: Probability × Impact
4
Priority
Classify as Low / Medium / High
5
Response
Choose: Avoid / Mitigate / Transfer / Accept
6
Risk Owner
Name the person responsible
7
Trigger
Define the early warning sign
RISK MANAGEMENT
35 / 45

## Slide 41
WORKED SOLUTION
Case Study Discussion — Sample Analysis
RISK:
College approval may be delayed.
Probability
4 / 5 — High
Impact
4 / 5 — High
Risk Score
16 — High Priority
Response
Mitigate
Owner
Project Manager
TRIGGER
Approval milestone missed by 3 days without explanation
MITIGATION
Schedule regular stakeholder reviews, maintain open communication with decision-makers
CONTINGENCY
Re-sequence development activities that do not require approval to maintain team productivity
RISK MANAGEMENT
36 / 45

## Slide 42
Common Risk Management Mistakes
WHAT TO AVOID
✕
Treating issues as risks
Future uncertainty and current problems need different management approaches.
✕
Focusing only on probability
A 10% chance of a ₹10 lakh loss outweighs a 90% chance of a ₹10,000 loss.
✕
No risk owner
If nobody owns it, nobody manages it — it will be forgotten.
✕
No trigger defined
Without an early warning sign, the team reacts instead of preparing.
✕
No contingency plan
Being unprepared when a risk occurs turns it into a crisis.
✕
One-time risk register
Risk is continuous. A register created once and never updated is useless.
✕
Ignoring opportunities
Positive risks deserve the same management attention as threats.
✕
Not communicating risks
Stakeholders cannot support response actions they do not know about.
✕
Creating a register too large
An enormous register with 200 risks is unmanageable. Prioritise ruthlessly.
✕
Confusing mitigation and contingency
Mitigation is before; contingency is after. They are not interchangeable.
RISK MANAGEMENT
37 / 45

## Slide 43
PMI REFERENCE
Key Concepts — Quick Reference
Risk
=
Uncertainty that can affect project objectives
Threat
=
Negative risk — could harm the project
Opportunity
=
Positive risk — could benefit the project
Probability
=
Likelihood of the risk occurring (1–5 or %)
Impact
=
Consequence if the risk occurs (1–5)
Risk Score
=
Probability × Impact — basis for prioritisation
Risk Owner
=
Named person responsible for managing the risk
Trigger
=
Early warning sign that the risk is approaching
Mitigation
=
Action to reduce probability or impact — before
Contingency
=
What we do if the risk occurs — after
Residual Risk
=
Risk remaining after the response is implemented
Secondary Risk
=
New risk created by implementing a response
RISK MANAGEMENT
38 / 45

## Slide 44
The Project Manager's Risk Questions
MINDSET
A good project manager never stops asking these questions throughout the project lifecycle.
1
What can go wrong?
2
How likely is it?
3
What happens if it does?
4
Which risks matter most?
5
What can we do now?
6
Who owns this risk?
7
What will tell us the risk is approaching?
8
What will we do if it happens?
9
What new risks have our actions created?
RISK MANAGEMENT
39 / 45

## Slide 45
FINAL TAKEAWAY · MODULE 4
Risk Management is
not predicting the future.
It is preparing the project to deal with uncertainty — before uncertainty becomes a crisis.
01
Identify
02
Analyse
03
Prioritise
04
Respond
05
Monitor
Good project managers don't wait for risks to become problems.
They prepare before uncertainty turns into an issue.
RISK MANAGEMENT
40 / 45